| Reference number To be filled in by the Executive Agency |  |
| --- | --- |

Application Form

| Note Programme | Culture (2007-2013) |
| --- | --- |
| Programme Guide | Programme Guide |
| Action | Strand 1.2.1 |
| Round | Period covered: 1 May 2009 – 30 November 2011 |
| Deadline | 1 Octobre 2008 |
| Project title (and acronym if any) |  |
| Application language |  |

The numbers in brackets refer to the Programme Guide

| Part A. Identification of the applicant (coordinator) of the project. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The parts A and B must be filled in for each co-organiser ('co-beneficiary') separately A separate copy regarding questions A1 to B3 is required for each organisation |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1 ORGANISATION |  |  |  |  |  |  |  |  |  |  |  |  |
| Role in the application |  |  | Coordinator |  |  |  |  |  |  |  |  |  |
|  |  |  | Co-organiser (Co-beneficiary) |  | N°1 N°2 N°3 N°4 N°5 N°6 N°… |  |  |  |  |  |  |  |
| Organisation's legal name: |  |  | Locus Sonus |  |  |  |  |  |  |  |  |  |
| Acronyme: |  |  |  |  |  |  |  |  |  |  |  |  |
| Department, if applicable: |  |  |  |  |  |  |  |  |  |  |  |  |
| Legal address: |  |  | Ecole Superieure d’art d’Aix en Provence, Rue Emile Tavan |  |  |  |  |  |  |  |  |  |
| Post Code: |  |  | 13100 | City: |  |  |  |  | Aix en Provence |  |  |  |
| Region: |  |  |  | Country: |  |  |  |  |  |  |  |  |
| Web site: |  |  | http://www.locusonus.org |  |  |  |  |  |  |  |  |  |
| Telephone: |  |  | 00 33 6 62 11 04 54 |  |  |  |  | Fax: |  |  |  |  |
| - A.2. PERSON AUTHORISED TO LEGALLY COMMIT THE ORGANISATION (LEGAL REPRESENTATIVE) |  |  |  |  |  |  |  |  |  |  |  |  |
| Surname: | Title | De Huer |  |  |  |  |  | First name: |  |  | Julie |  |
| Position: |  | President |  |  |  |  | Telephone: |  |  | 00 33 6 62 11 04 54 |  |  |
| A.3. PERSON RESPONSIBLE FOR THE IMPLEMENTATION OF THE ACTION (CONTACT PERSON) |  |  |  |  |  |  |  |  |  |  |  |  |
| Surname: | Title | Roquigny |  |  |  | First name: |  |  |  |  | Anne |  |
| Position: |  | coordination |  |  |  |  |  |  |  |  |  |  |
| E-mail: |  | anne@roquigny.info |  |  |  |  |  |  |  |  |  |  |
| Telephone: |  | 00 33 6 62 11 04 54 |  |  |  |  |  | Fax: |  |  |  |  |

| Part B. Organisation and activities |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The candidate should refer to the applicable eligibility criteria as stated in the Programme Guide |  |  |  |  |  |  |  |  |  |
| B.1. STRUCTURE |  |  |  |  |  |  |  |  |  |
| Legal Status: | Public |  |  | Private |  |  |  |  |  |
|  | Profit |  |  | Non-profit |  |  | Charity |  |  |
| Type of the organisation: | National authority |  | Regional authority | Local authority |  | NGO |  | Cultural enterprise | Opera |
|  | University |  | School | Museum |  | Theatre |  | Network |  |
| Registered Office: |  |  |  |  |  |  |  |  |  |
| B.2. OBJECTIVES AND ACTIVITIES OF THE ORGANISATION (not applicable for municipalities and universities) |  |  |  |  |  |  |  |  |  |
| Please provide a short presentation of your organisation or group (usual activities, affiliations, etc) in relation to the field covered by the project. Locus Sonus is a research laboratory in audio art. Its objective is to experiment the innovative and multidisciplinary aspects of the sound artistic forms, by assuring the mission to create a corpus of knowledge and a criticize space towards the activities and the practices in audio art which is in full evolution in a strong technological and socio-technical context. This laboratory proposes processes of work, research and realization which combine the practical experiment and the evaluation criticizes by questioning collectively the sound environments according to two axes: audio in space, audio in network. |  |  |  |  |  |  |  |  |  |
| Please provide a presentation of your motivation in the field covered by the project. Today, Locus Sonus is involved in the construction of artistic forms (installations and performances - in a wide sense) and in devices of interactions and correlations around the notion of field spatialization, networked spaces, by emphasizing the reflection and the practices connected to the stake in sound space with multiple scales- going of the streaming to the acoustics, the telephony, the radiotelephony, and to the virtual spaces- In the mobilization of the personal sound space and in the notions of stream in the sound artistic representation. |  |  |  |  |  |  |  |  |  |
| B.3. OTHER COMMUNITY FUNDING |  |  |  |  |  |  |  |  |  |
| The Executive Agency should be informed of any future application or funding Will your organisation or group apply for or receive funding from the European Union for the last financial exercise? If yes, for every subsidy, please indicate the activity, the Directorate-General, the programme concerned and the allocated amount: |  |  |  |  |  |  |  |  |  |
| Activity |  | Directorate-General |  |  | Programme Concerned |  |  | Subsidy Allocated/Requested |  |

| PART C. Description of the project |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C.1. Calendar of the project |  |  |  |  |  |  |  |  |  |  |  |
| Project start date (I.8): 01 /05 /2009 Project end date: 01 /05 /2011 Project duration (IV.4.2): 24 months |  |  |  |  |  |  |  |  |  |  |  |
| C.2. Please specify which are the different European countries (indicated in alphabetical order of the ISO-Codes) participating in the Programme that will host and/or benefit from the activities: |  |  |  |  |  |  |  |  |  |  |  |
|  | AT | Austria |  |  |  | LI |  | Liechtenstein |  |  |  |
|  | BE | Belgium |  |  |  | LT |  | Lithuania |  |  |  |
|  | BG | Bulgaria |  |  |  | LU |  | Luxembourg |  |  |  |
|  | CY | Cyprus |  |  |  | LV |  | Latvia |  |  |  |
|  | CZ | Czech Republic |  |  |  | MK |  | The Former Yugoslav Republic of Macedonia |  |  |  |
|  | DE | Germany |  |  |  | MT |  | Malta |  |  |  |
|  | DK | Denmark |  |  |  | NL |  | Netherlands |  |  |  |
|  | EE | Estonia |  |  |  | NO |  | Norway |  |  |  |
|  | ES | Spain |  |  |  | PL |  | Poland |  |  |  |
|  | FI | Finland |  |  |  | PT |  | Portugal |  |  |  |
|  | FR | France |  |  |  | RO |  | Romania |  |  |  |
|  | GR | Greece |  |  |  | RS |  | Serbia |  |  |  |
|  | HR | Croatia |  |  |  | SE |  | Sweden |  |  |  |
|  | HU | Hungary |  |  |  | SI |  | Slovenia |  |  |  |
|  | IE | Ireland |  |  |  | SK |  | Slovakia |  |  |  |
|  | IS | Iceland |  |  |  | TR |  | Turkey |  |  |  |
|  | IT | Italy |  |  |  | UK |  | United Kingdom |  |  |  |
| C.3. Organisations (please add further rows as necessary) (IV.1) |  |  |  |  |  |  |  |  |  |  |  |
| Role |  |  |  | Name of the organisation |  |  | When was your organisation legally established |  | Number of permanent staff employed by the organisation |  | Country (ISO Code) |
|  |  |  |  |  |  |  |  |  | Part time | Full time |  |
| Coordinator |  |  |  | Locus Sonus |  |  |  |  | 3 |  | FR |
| Co-organiser n°1 |  |  |  | SARC |  |  |  |  |  |  | GB |
| Co-organiser n°2 |  |  |  | CRISAP |  |  |  |  |  |  | GB |
| Co-organiser n°3 |  |  |  | KIBLA |  |  |  |  |  |  | SI |
| Co-organiser n°4 |  |  |  | LORNA |  |  |  |  |  |  | IS |
| Co-organiser n°5 |  |  |  |  |  |  |  |  |  |  |  |
| Co-organiser n°6 |  |  |  |  |  |  |  |  |  |  |  |
| Are there dependencies between the organisation and the co-organisers involved in this application (coordinator / co-organisers or co-organiser / co-organiser)? (see for examples of dependencies on the website of the Agency under Frequently Asked Questions) |  |  |  |  |  |  |  |  |  |  |  |
| No |  |  |  |  |  |  |  |  |  |  |  |
| Yes (please specify) |  |  |  |  |  |  |  |  |  |  |  |

| C.4 Relevance to the specific objectives of the Programme (I.4.1) |  |  |  |
| --- | --- | --- | --- |
| Objectives of the programme (please tick as appropriate) |  |  |  |
| - The project supports the trans-national mobility of people working in the cultural sector |  |  |  |
| - The project encourages the trans-national circulation of artistic and cultural works and products |  |  |  |
| - The project encourages intercultural dialogue |  |  |  |
| Field (Please tick the relevant box) |  | Priority (please indicate 1, 2, 3 following the priority if your project is interdisciplinary) |  |
| - Cultural Heritage |  |  |  |
| - Visual Arts |  |  |  |
| - Performing Arts |  |  |  |
| - Literature, Books and Reading |  |  |  |
| - Architecture |  |  |  |
| - Design, Applied Arts |  |  |  |
| - Interdisciplinary (if it is an interdisciplinary project, - only click this box and indicate in the second column - the specific area including the order of priority) |  |  |  |
| Please specify how your project relates to the objectives and selected fields. The main part of the project is to offer a framework for research and experimentation by encouraging the mobility of researchers and artists between partner organizations. By organizing symposiums and workshops, we assure a cooperation between different organizations in different member’s states of EU and share our knowledge concentrating on inter-cultural contexts of the sound network. These activities of reflection are profoundly fed by a will of our part, to work on a precise theme in a process of cooperation linked to the cultural context of each partners co-organizers and associated. The other part of the project is to organize an intercultural dialogue, fed by various experiences, researches on the subject of sounds in network, to revitalize the already begun researches. Furthermore, our activities are developed on a will to put in relation, via sound, different places of the European territory. Although it is not explicit, this appropriation of places by the public will have for consequence an emotional and imaginary journey, having for only source the sound, to the other places, the other cultures. On the criterion of the artistic works circulation, the installation «locustream Promenade” (artistic installation) is planned to circulate to 5 different cities (the cities of the partners co-organizers, Paris, London, Belfast, Reykjavik and Maribor). In parallel, another artistic installation is planned to circulate between three towns of our associated partners (see detailed presentation of the project). |  |  |  |
| C.5 Activities most relevant to the project |  |  |  |
| Performance |  |  |  |
| Dance |  |  |  |
| Theatre |  |  |  |
| Music |  |  |  |
| Opera |  |  |  |
| Street Art |  |  |  |
| Fair/Exhibition |  |  |  |
| Festival |  |  |  |
| Publication |  |  |  |
| Research |  |  |  |
| Training |  |  |  |
| Conference/ Seminar/ Workshop |  |  |  |
| Multimedia and new technologies |  |  |  |
| Innovation and Creativity (European Year in 2009) |  |  |  |
| Other (please specify) |  |  |  |

C.6 Summary of the project in English, or French, or German (max. 2000 Characters).

The project we are proposing is a multidisciplinary co-operation, combining artistic practices and basic research on sound, network audio and architecture geographic space. The principle behind the project is to investigate and develop artistic possibilities on the intersection of networked and acoustic or local audio spaces, through the use of streaming techniques, and more generally the use of flux for artistic purposes (flux understood here as a continually updating medium). The research is organized under two main thematics Field Spatialization and Networked Sonic Spaces. The research, fundamentally practice based, aims to create a corpus of artistic experimentation around a problematic, common to all the partners. Forms emanating from this activity are « verified » essentially through their presentation in public contexts. The choice of implementing this research within the art education environment is prompted by the current renewal of techniques and art-forms which are at the intersection of the visual arts and music.

| PART D: Operational capacity |  |  |  |  |
| --- | --- | --- | --- | --- |
| D.1 Experience in cultural cooperation with organisations from eligible countries under the Culture Programme (I.3.2) |  |  |  |  |
| Please indicate only experience of he past three years |  |  |  |  |
| Country | Name of the organisation | Year |  | Project title |
|  |  | From | To |  |

| PART E: Implementation of the project/Award criteria |  |  |  |
| --- | --- | --- | --- |
| E.1. Detailed description of the project (between 15.000 – 20.000 characters, i.e. maximum 5 pages Please note: This section of the application form will be used to evaluate your proposal on the basis of the award criteria (i.e. European added value, relevance to the specific objectives of the Programme, excellence of proposed cultural activities). |  |  |  |
| E.2. Quality of partnership Please describe the method of management applied to the project (cooperation scheme with co-organisers, i.e. contacts, meetings, monitoring of activities). |  |  |  |
|  | Conceptual role (brief description): | Implementation role (brief description): | Financial contribution in EURO: |
| - coordinator: - coorganiser N° 1: - coorganiser N° 2: - coorganiser N° 3: - coorganiser N° 4: - coorganiser N° 5: - coorganiser N° 6: |  |  |  |

| If you have associated partners, what will be their role (i.e. tasks)? |  |  |  |
| --- | --- | --- | --- |
| - Implementation role (brief description): - associated partner N° 1: STEIM, (Amsterdam) Center for research & development of instruments & tools for performers in the electronic performance arts. http://www.steim.org/ Contact Tarek Atoui atouitarek@yahoo.fr & Takuro Mizuta Lippit djsniff@gmail.com - associated partner N° 2: MEDIALAB PRADO (Madrid , Spain) http://www.medialab-prado.es/ Contact : Marcos García : marcos@medialab-prado.es - associated partner N° 3: HANGAR (Barcelona , Spain) http://www.hangar.org/ contact : Pedro Solers pedro@hangar.org - associated partner N° 4: CULTURELAB (Newcastle, England) http://www.ncl.ac.uk/culturelab contact Atau Tanaka : atau.tanaka@ncl.ac.uk |  |  |  |
| E.3. Expected level of outputs - What are the expected outputs, both tangible and intangible, of your activities (III.10)? - Please specify who and how many people might benefit directly and indirectly from the results of the proposed activities? - Please explain the trans-sectorial (i.e. interdisciplinary) dimension where relevant of your project and the potential for interaction between different artistic and cultural domains (i.e. performing arts, visual arts, cultural heritage, design and applied arts, literature, architecture, new media)? |  |  |  |
| Target group: General public Youth Artists Minority Disadvantaged people Culture specialists/experts Educational institution |  |  |  |
| E.4. Communication and promotion activities (III.10) - How do you intend to disseminate the results of your activities? - How do you intend to promote the visibility of the European Union through your project? - Could you please detail your communication and promotion plan? |  |  |  |
| - Which are the different communication tools used for your communication and promotion plan? |  |  |  |
| Media | Number of Media | People Targeted | How many people |
| TV |  |  |  |
| Radio |  |  |  |
| Written press |  |  |  |
| Internet |  |  |  |
| Publications |  |  |  |
| Merchandising |  |  |  |

E.5. Sustainability - How can the proposed activities result in continued/sustained cooperation, in complementary activities and/or permanent benefits at European level? How can the project contribute to a longer-term development of cultural cooperation in Europe? - What is the potential of the proposed activities to generate other future initiatives of cultural cooperation at European or regional level?

| PART F: TIMETABLE FOR THE IMPLEMENTATION OF THE PROJECT ACTIVITIES |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Please fill in the following table in accordance with the detailed description of the project activities in point E.1 |  |  |  |  |  |  |  |  |
| Project start date |  |  | Project end date |  |  |  |  |  |
| N° | Activity (brief description) |  | From (m/yyyy) | To (m/yyyy) | Location | Name of coordinator/co-organiser(s) responsible and involved | Subcontracting (tick if appropriate) (III.5) | Name of subcontractor (if known) |
| 1 | Coordination Meeting with the co-organisers |  | May 2009 | Mai 2009 | Aix en Provence, France | Peter Sinclair, Jérôme Joy, Locus Sonus |  |  |
| 2 | Coordination Meeting co-organisers and associated partners + Organisation of the project, scientific comittee + Symposium + Presentation of the Locustream Promenade |  | Sept 2009 | Sept 2009 | London, UK | Angus Carlyle CRISAP |  |  |
| 3 | Presentation of Locus AudioTardis or Lucus Tuner |  | Nov 2009 | Nov 2009 | Madrid, Spain | - Marcos Garcia Medialab Prado |  |  |
| 4 | Coordination Meeting co-organisers and associated partners + Organisation of the project, scientific comittee + Workshop+ Presentation of the Locustream Promenade |  | Janv 2010 | Janv 2010 | Maribor, Slovenia | Peter Tomaz Dobrila, Kibla |  |  |
| 5 | Presentation of Locus AudioTardis or Lucus Tuner |  | Mars 2010 | Mars 2010 | Newcastle, UK | Atau Tanaka, Culture Lab |  |  |
| 6 | Coordination Meeting co-organisers and associated partners + Organisation of the project, scientific comittee + Workshop+ Presentation of the Locustream Promenade |  | May 2010 | May 2010 | Reykjavik, Iceland | Ragnar helgi Olafsson |  |  |
| 7 | Presentation of Locus AudioTardis or Lucus Tuner |  | July 2010 | July 2010 | Rotterdam, Netherlands | Takuro Mizuta Lippit |  |  |
| 8 | + Organisation of the project, scientific comittee + Workshop+ Presentation of the Locustream Promenade |  | Sept 2010 | Sept 2010 | Belfast ,Ireland | Pedro Rebelo + Alain Renaud |  |  |
|  | Coordination Meeting co-organisers and associated partners + Organisation of the project, scientific comittee + Symposium + Presentation of the Locustream Promenade |  | Janv 2011 | JAnv 2011 | Nice, France | Peter Sinclair, Jérôme Joy, Locus Sonus |  |  |
| 9 | Presentation of Locus AudioTardis or Lucus Tuner |  | Mars 2011 | Mars 2011 | Barcelone, Hangar | Pedro Solers |  |  |
| 10 | Final Meeting |  | May 2011 | May 2011 | Maribor, Slovenia | Peter Tomas Dobrila |  |  |

Please add further rows as necessary

PART G: INFORMATION ON THE PROJECT – ESTIMATED BUDGET (III)

Please fill in and attach the budget form (EXCEL format)

After having filled in the attached budget form, you should indicate the total amount of the expenditures, of the income and of the requested grant in the following boxes in Euro:

Total expenditures

Total income

Grant requested

Applicants are reminded that total income should equal total expenditure. The grant requested has to be included in the total income.

Declaration on honour

To be completed by the person legally authorised to sign on behalf of the applicant organisation

I, the undersigned, hereby request a grant for 2009 from the Education, Audiovisual and Culture Executive Agency of EUR ………… for the operating costs covered by this grant application. I, the undersigned, certify that all information contained in this application, including the description of the work programme, is correct to the best of my knowledge and that I am aware of the content of the annexes to the application form. I confirm that my institution/organisation has the financial and operational capacity to complete the proposed project. I take note that under the provisions of the Financial Regulation applicable to the general budget of the European Communities, grantsmay not be awarded to applicants who are in any of the following situations: - are bankrupt or being wound up, are having their affairs administered by the courts, have entered into an arrangement with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations; - have been convicted of an offence concerning their professional conduct by a judgment which has the force of res judicata; - have been guilty of grave professional misconduct proven by any means which the contracting authority can justify; - have not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those of the country of the contracting authority or those of the country where the contract is to be performed; - have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the Communities' financial interests; - following another procurement procedure or grant award procedure financed by the Community budget, have been declared to be in serious breach of contract for failure to comply with their contractual obligations; - in their grant application, are subject to a conflict of interest; - in their grant application, are guilty of misrepresentation in supplying the information required by the contracting authority as a condition of participation in the grant award procedure, or fail to supply this information. I confirm that neither I nor the institution for which I am acting as legal representative are in any of the situations described above, and that I am aware that the penalties set out in the Financial Regulation may be applied in the case of a false declaration. In the event that my grant application is successful, I authorise the Commission / the Agency to publish on its website or in any other appropriate medium: - the name and address of the beneficiary of the grant; for networks, the name and address of the members; - the subject of the grant; - the amount awarded and the rate of funding of the costs of the approved work programme. By signing this application form, I accept all the conditions set out in the Culture Programme (2007-2013) Programme Guide, including the general conditions of the European Commission published on the Executive Agency website.

Done at: Date / / (day/month/year) Contractor's signature Stamp of the applicant organisation / Name and position in capitals:

This part must be completed by the coordinator and by each co-organiser ('co-beneficiary') separately

CHECKLIST FOR THE ANNEXES

| ANNEX.A | Activity Report of the past two (2) years (II.2.3.1) | YES |  |
| --- | --- | --- | --- |

| ANNEX B | Curriculum Vitae (II.2.3.1) | YES |  |
| --- | --- | --- | --- |

| ANNEX C | Legal Entity Identification form to be downloaded at the following website: http://europa.eu.int/comm/budget/execution/legal_entities_en.htm + documents attesting to the legal status of the entity (for the coordinator only) (II.2.1.1) | YES |  |
| --- | --- | --- | --- |

| ANNEX D | Financial Identification Form (for the coordinator only) | YES |  |
| --- | --- | --- | --- |

| ANNEX E | Official accounts (Balance sheets + Profit/Loss accounts) (for the coordinator only) | YES |  |
| --- | --- | --- | --- |

| ANNEX F | Financial Capacity form (for the coordinator only) (II.2.3.1) | YES |  |
| --- | --- | --- | --- |

| ANNEX G | Mandate (for co-organisers only) | YES |  |
| --- | --- | --- | --- |

| ANNEX H | Budget form | YES |  |
| --- | --- | --- | --- |

NOTE: For each annex please use a divider

The Programme Guide published on the website of the Agency explains the conditions for application. Where necessary, this form refers back to the Programme Guide. See for example point C.3 of this application form: the reference to the Programme Guide = (IV.1).

This email address will be used for all kind of correspondence including the acknowledgment of receipt.

Please specify if it is a dance, theatre, music, opera, street art performance; a fair/exhibition; a festival; a publication; a research, a training, a conference/seminar/workshop; a multimedia and new technologies; an innovation and creativity (European Year in 2009) or other.

Council Regulation (EC, Euratom) No 1605/2002 (OJ L 248 of 16.09.2002), amended by Regulations (EC, Euratom) No 1995/2006 (OJ L 390 of 30.12.2006) and (EC) No 1525/2007 (OJ L 343 of 27.12.2007). These can be consulted in the Official Journal online at: http://europa.eu.int/eur-lex/lex/en/index.htm